## README
Python-Integrated Critical Path & Gantt Scheduler
By Zhijing Eu ¦ Ver 1.3 candidate ¦ 19 Oct 2026
This workbook provides a lightweight project scheduling model using Python in Excel and Critical Path Method (CPM) logic.
Disclosure : This workbook was generated partly with AI coding support from Microsoft Copilot and ChatGPT 6.1 Sol Light
Enter task durations, dependencies, progress and fixed-date constraints in the Workplan tab. The scheduling engine calculates task dates, finish float and the critical path, while the weekly Gantt provides a visual view of the resulting schedule.
1. WORKPLAN INPUTS
TaskID
Unique identifier for each task, milestone or summary task. TaskIDs must be unique and are used when defining predecessor relationships.
TaskType
Use one of three values:
• Activity – A normal scheduled activity with a defined duration.
• Milestone – A zero-duration event occurring on a single date.
• Summary – A hammock task whose Start, Finish and CalcDuration are dynamically determined from other tasks.
Duration
Task duration in weeks.
Enter a nonnegative duration for Activities. Blank durations retain the original zero-duration convention.
• Milestones have zero duration.
• Summary duration is calculated automatically from its SS and FF anchors.
Progress
Current task completion percentage, for information only. Progress does not affect dates or float.
Enter as a percentage or decimal, for example 50% or 0.5.
Predecessors
Defines the scheduling relationships between tasks.
Supported relationships:
• FS – Finish-to-Start
• SS – Start-to-Start
• FF – Finish-to-Finish
Multiple predecessors are separated by commas.
Examples:
001 FS
002 FS, 003 FS
008 SS+2
026 FS-2
Positive and negative lags are expressed in weeks.
Constraints
Optional fixed Start date.
When populated, the Constraint establishes the task’s Start date rather than allowing predecessor logic alone to determine it.
Constraints override early starts only. Late dates and float are not pinned to fixed dates; positive float is not permission to miss a fixed date.
2. SUMMARY / HAMMOCK TASKS
Summary tasks represent the elapsed window between underlying activities.
Leave Duration blank or zero and define the boundaries through the Predecessors field.
Example:
001 SS, 005 FF
This means:
• Summary Start = Start of 001
• Summary Finish = Finish of 005
• CalcDuration = Summary Finish minus Summary Start
Multiple SS and FF anchors can be provided. The Summary uses the earliest SS boundary and latest FF boundary.
Summaries are visual groupings, excluded from criticality. Their anchors must be Activities or Milestones; nested Summaries are not supported.
3. CALCULATED SCHEDULE FIELDS
The following fields are generated by the Python scheduling engine and should not be manually edited.
CalcDuration
Calculated duration in weeks.
For Activities, this normally equals Duration. For Summary tasks, it represents the dynamically calculated hammock span.
Start / Finish
Calculated calendar Start and Finish dates based on predecessor relationships, durations and any applicable fixed constraints.
EarlyStart / EarlyFinish
Underlying CPM schedule positions expressed as elapsed weeks from the scheduling origin.
These primarily support the scheduling calculation rather than normal user interpretation.
TotalFinishFloat
Calculated as Late Finish minus Early Finish.
LateStart / LateFinish (V:W) are week offsets for activities and milestones. TotalFinishFloat = LateFinish - EarlyFinish = LateStart - EarlyStart. FreeFloat (X) respects dependency endpoints/lags and the current project finish. Hammocks have blank late dates/float. Negative values flag conflicts. Fixed dates remain forward-only overrides.
• 0 = Critical Path
Greater than 0 = float relative to the calculated project finish, subject to the fixed-date limitation.
• Less than 0 = negative float / schedule conflict
Activities and Milestones participate in float/criticality analysis. Summary tasks do not.
IsCritical
Flags Activities and Milestones whose TotalFinishFloat is effectively zero or negative.
A negative-float flag can indicate a conflict. Milestones still use the diamond chart symbol regardless of their critical flag.
4. WEEKLY GANTT
The weekly Gantt is generated from the calculated Start and Finish dates.
Each column represents one week. The chart displays 63 weeks from the earliest task start; longer schedules can continue beyond the visible chart.
Symbols mean:
X Activity with effectively zero or negative float; inspect negative float and constraint warnings.
O Non-Critical Activity
◆ Milestone
= Summary / Hammock
Activities and Summaries appear in each weekly column that overlaps their calculated Start-to-Finish period.
Milestones appear once in the week containing their milestone date.
5. USING THE WORKBOOK
Enter up to 100 tasks consecutively from row 3. Do not leave gaps or sort input/output columns together. Trailing blank rows are allowed.
Enter Duration, Predecessors and any fixed Constraints.
Allow Python in Excel to recalculate the schedule.
Review dates and float, the Workplan status banner, and ScheduleWarning in column CL. Do not use cached outputs after a Python error.
Review the weekly Gantt for sequencing, overlaps, milestones, Summary spans and Critical Path Activities.
When changing dependency logic, use valid TaskIDs and relationship syntax consistently.
6. IMPORTANT NOTES
Use at your own risk. This lightweight planning aid is not a comprehensive scheduling or assurance tool.
Do not manually overwrite Python-generated schedule outputs.
Summary tasks need SS and FF anchors to Activities/Milestones. Cycles, invalid inputs, and nested Summaries stop calculation.
Fixed starts override dependencies. Conflicts are shown as warnings while the overridden schedule remains visible.
Float ignores fixed dates in the backward pass. Resolve date conflicts before relying on the schedule.
Activities and Milestones are classified as Critical or Non-Critical. Summaries are excluded.
Weekly view with simple elapsed time; no custom working/holiday calendars or comprehensive progress calculations.
Requires internet access and eligible Microsoft 365 Python in Excel. Python inputs run in Microsoft cloud services. Verify calculation completes after edits.
7. TROUBLESHOOTING
Sometimes you may encounter calculation errors with the Python Cells.
Under Formula -use the (F9) Calculate Now or (Shift+F9) Calculate Sheet
If that does not work - try the Reset button in the Python option
#VALUE!
Note that depending on your license , Microsoft does impose monthly Premium compute allowance limits , once exhausted, calculations will continue but at (a slightly slower) standard speed.
#VALUE!

## Planning Assumptions
Key Planning Assumptions
# | Description
1
2
3
4
5
6
7
8
9
10

## Workplan
No constraint conflicts detected. Float ignores fixed dates. See README. | time axis 2026-10-20 to 2027-12-28
TaskID | TaskType | Stage | TaskTitle | TaskDescription | Task Grouping A | Task Grouping B | Task Grouping C | Task Grouping D | Duration | Progress | Predecessors | Constraints | #VALUE! | #VALUE! | CalcDuration | Start | Finish | EarlyStart | EarlyFinish | LateStart | LateFinish | FreeFloat | TotalFinishFloat | IsCritical | [63 empty] | ScheduleWarning
0010 | Summary |  | Build a house | [5 empty] | 0 |  | 0020 SS,0230 FF |  |  |  | 60 | 2026-10-20 | 2027-12-14 | 0 | 60 |  |  |  |  | FALSE | bar: 2026-10-20 to 2027-12-07
0020 | Milestone |  | Start Build | [5 empty] | 0 |  |  | 2026-10-20 |  |  | 0 | 2026-10-20 | 2026-10-20 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | bar: 2026-10-20
0030 | Activity |  | PREPARE SITE | [5 empty] | 4 |  | 0020 FS |  |  |  | 4 | 2026-10-20 | 2026-11-17 | 0 | 4 | 0 | 4 | 0 | 0 | TRUE | bar: 2026-10-20 to 2026-11-10
0040 | Activity |  | ERECT HOARDING | [5 empty] | 2 |  | 0030 FS |  |  |  | 2 | 2026-11-17 | 2026-12-01 | 4 | 6 | 5 | 7 | 0 | 1 | FALSE | bar: 2026-11-17 to 2026-11-24
0050 | Activity |  | EXCAVATE FOUNDATION | [5 empty] | 7 |  | 0030 FS |  |  |  | 7 | 2026-11-17 | 2027-01-05 | 4 | 11 | 4 | 11 | 0 | 0 | TRUE | bar: 2026-11-17 to 2026-12-29
0060 | Activity |  | LAY DRAINS | [5 empty] | 4 |  | 0040 FS |  |  |  | 4 | 2026-12-01 | 2026-12-29 | 6 | 10 | 7 | 11 | 1 | 1 | FALSE | bar: 2026-12-01 to 2026-12-22
0070 | Activity |  | CONCRETE FOUNDATION | [5 empty] | 5 |  | 0050 FS,0060 FS |  |  |  | 5 | 2027-01-05 | 2027-02-09 | 11 | 16 | 11 | 16 | 0 | 0 | TRUE | bar: 2027-01-05 to 2027-02-02
0080 | Activity |  | BRICKWORK | [5 empty] | 9 |  | 0070 FS |  |  |  | 9 | 2027-02-09 | 2027-04-13 | 16 | 25 | 16 | 25 | 0 | 0 | TRUE | bar: 2027-02-09 to 2027-04-06
0090 | Activity |  | INSTALL WINDOWS | [5 empty] | 6 |  | 0080 SS+2 |  |  |  | 6 | 2027-02-23 | 2027-04-06 | 18 | 24 | 19 | 25 | 1 | 1 | FALSE | bar: 2027-02-23 to 2027-03-30
0100 | Activity |  | ROOF TRUSSES | [5 empty] | 6 |  | 0080 FS,0090 FS |  |  |  | 6 | 2027-04-13 | 2027-05-25 | 25 | 31 | 25 | 31 | 0 | 0 | TRUE | bar: 2027-04-13 to 2027-05-18
0110 | Activity |  | ROUGH PLUMBING & ELECTRIC | [5 empty] | 4 |  | 0100 SS+2 |  |  |  | 4 | 2027-04-27 | 2027-05-25 | 27 | 31 | 34 | 38 | 7 | 7 | FALSE | bar: 2027-04-27 to 2027-05-18
0120 | Activity |  | ROOF FINISH | [5 empty] | 7 |  | 0100 FS |  |  |  | 7 | 2027-05-25 | 2027-07-13 | 31 | 38 | 31 | 38 | 0 | 0 | TRUE | bar: 2027-05-25 to 2027-07-06
0130 | Activity |  | LANDSCAPING | [5 empty] | 4 |  | 0150 SS |  |  |  | 4 | 2027-07-13 | 2027-08-10 | 38 | 42 | 55 | 59 | 17 | 17 | FALSE | bar: 2027-07-13 to 2027-08-03
0140 | Summary |  | PLASTER WALLS | [5 empty] | 0 |  | 0150 SS,0170 FF |  |  |  | 12 | 2027-07-13 | 2027-10-05 | 38 | 50 |  |  |  |  | FALSE | bar: 2027-07-13 to 2027-09-28
0150 | Activity |  | WALL A | [5 empty] | 2 |  | 0110 FS,0120 FS |  |  |  | 2 | 2027-07-13 | 2027-07-27 | 38 | 40 | 38 | 40 | 0 | 0 | TRUE | bar: 2027-07-13 to 2027-07-20
0160 | Activity |  | WALL B | [5 empty] | 3 |  | 0150 FS+3 |  |  |  | 3 | 2027-08-17 | 2027-09-07 | 43 | 46 | 43 | 46 | 0 | 0 | TRUE | bar: 2027-08-17 to 2027-08-31
0170 | Activity |  | WALL C | [5 empty] | 2 |  | 0160 FS+2 |  |  |  | 2 | 2027-09-21 | 2027-10-05 | 48 | 50 | 48 | 50 | 0 | 0 | TRUE | bar: 2027-09-21 to 2027-09-28
0180 | Activity |  | FINISH ELECTRICS | [5 empty] | 4 |  | 0170 FS |  |  |  | 4 | 2027-10-05 | 2027-11-02 | 50 | 54 | 50 | 54 | 0 | 0 | TRUE | bar: 2027-10-05 to 2027-10-26
0190 | Activity |  | FINISH PLUMBING | [5 empty] | 4 |  | 0170 FS |  |  |  | 4 | 2027-10-05 | 2027-11-02 | 50 | 54 | 50 | 54 | 0 | 0 | TRUE | bar: 2027-10-05 to 2027-10-26
0200 | Activity |  | DECORATE | [5 empty] | 4 |  | 0180 FS, 0190 FS |  |  |  | 4 | 2027-11-02 | 2027-11-30 | 54 | 58 | 54 | 58 | 0 | 0 | TRUE | bar: 2027-11-02 to 2027-11-23
0210 | Activity |  | CLEAN DOWN | [5 empty] | 1 |  | 0200 FS |  |  |  | 1 | 2027-11-30 | 2027-12-07 | 58 | 59 | 58 | 59 | 0 | 0 | TRUE | bar: 2027-11-30
0220 | Activity |  | SNAGGING | [5 empty] | 1 |  | 0130 FS ,0210 FS |  |  |  | 1 | 2027-12-07 | 2027-12-14 | 59 | 60 | 59 | 60 | 0 | 0 | TRUE | bar: 2027-12-07
0230 | Milestone |  | Build Complete | [5 empty] | 0 |  | 0220 FS |  |  |  | 0 | 2027-12-14 | 2027-12-14 | 60 | 60 | 60 | 60 | 0 | 0 | TRUE | bar: 2027-12-14

## Python Formulas In WorkplanTab
Reference ONLY - These are NOT Live Cells
Cell 02 | import re d=xl("A2:M1037",headers=True) # Outputs spill consecutively from row 3, so task inputs must be consecutive. present=d["TaskID"].notna() populated=d.astype(object).where(d.notna(),"").astype(str).apply(lambda c:c.str.strip().ne("")).any(axis=1) missing=populated & ~present if missing.any(): raise ValueError("Missing TaskID on input row(s): "+", ".join(str(i+3) for i in np.flatnonzero(missing.to_numpy()))) positions=np.flatnonzero(present.to_numpy()) if len(positions) and not present.iloc[:positions[-1]+1].all(): raise ValueError("Remove blank task-row gaps: enter tasks consecutively from row 3") if len(positions)>100: raise ValueError("This template displays at most 100 task rows; shorten the schedule or use a larger scheduling tool") d=d.dropna(subset=["TaskID"]).copy() if d.empty: raise ValueError("Enter at least one task") d["TaskID"]=d["TaskID"].astype(str).str.strip() if d["TaskID"].eq("").any(): raise ValueError("TaskID cannot be whitespace") d["TaskType"]=d["TaskType"].fillna("Activity").astype(str).str.strip().str.capitalize() raw_duration=d["Duration"] number_duration=pd.to_numeric(raw_duration,errors="coerce") nonblank=raw_duration.notna() & raw_duration.astype(str).str.strip().ne("") bad_duration=nonblank & (number_duration.isna() ¦ ~np.isfinite(number_duration) ¦ number_duration.lt(0)) if bad_duration.any(): raise ValueError("Duration must be a finite nonnegative number for: "+", ".join(d.loc[bad_duration,"TaskID"])) d["Duration"]=number_duration.fillna(0) d["Predecessors"]=d["Predecessors"].fillna("").astype(str).str.strip() T=d["TaskID"].tolist() typ=dict(zip(T,d["TaskType"])) rawdur=dict(zip(T,d["Duration"])) valid_types={"Activity","Milestone","Summary"} bad_types=[t for t in T if typ[t] not in valid_types] if bad_types: raise ValueError("Invalid TaskType for: "+", ".join(bad_types)) if len(T)!=len(set(T)): raise ValueError("Duplicate TaskID found") dur={ t:0.0 if typ[t] in ("Milestone","Summary") else float(rawdur[t]) for t in T } dates=pd.to_datetime(d["Constraints"],errors="coerce",dayfirst=True) nonblank_date=d["Constraints"].notna() & d["Constraints"].astype(str).str.strip().ne("") bad_date=nonblank_date & dates.isna() if bad_date.any(): raise ValueError("Invalid Constraint date for: "+", ".join(d.loc[bad_date,"TaskID"])) valid=dates.dropna() if valid.empty: raise ValueError("At least one Constraint date is required") origin=valid.min().normalize() fix={} for i,r in d.iterrows(): x=dates.loc[i] fix[r["TaskID"]]=( None if pd.isna(x) else (x.normalize()-origin).days/7 ) pred={t:[] for t in T} succ={t:[] for t in T} pat=re.compile( r"^\s*(\S+)\s+(FS¦SS¦FF¦SF)" r"(?:\s*([+-])\s*(\d+(?:\.\d+)?))?\s*$", re.I ) for r in d.itertuples(): if not r.Predecessors: continue for text in r.Predecessors.split(","): text=text.strip() m=pat.match(text) if not m: raise ValueError("Invalid predecessor: "+text) p,rel,sg,n=m.groups() rel=rel.upper() if p not in T: raise ValueError("Unknown predecessor: "+p) if typ[p]=="Summary": raise ValueError(r.TaskID+" cannot depend on Summary task "+p) if p==r.TaskID: raise ValueError("Task cannot depend on itself: "+p) lag=float(n or 0) if sg=="-": lag=-lag pred[r.TaskID].append((p,rel,lag)) if typ[r.TaskID]!="Summary": succ[p].append((r.TaskID,rel,lag)) for t in T: if typ[t]=="Summary": invalid=[rel for p,rel,lag in pred[t] if rel not in ("SS","FF")] if invalid: raise ValueError( t+" Summary only supports SS and FF anchors" ) # Reject all dependency cycles, including zero-lag SS cycles. degree={t:len(pred[t]) for t in T} following={t:[] for t in T} for t in T: for p,rel,lag in pred[t]: following[p].append(t) ready=[t for t in T if degree[t]==0] for p in ready: for t in following[p]: degree[t]-=1 if degree[t]==0: ready.append(t) if len(ready)!=len(T): raise ValueError("Dependency cycle detected; check: "+", ".join(t for t in T if degree[t]>0)) if all(typ[t]=="Summary" for t in T): raise ValueError("Enter at least one Activity or Milestone") (T,typ,dur,fix,pred,succ,origin) | Cell P2 | T,typ,dur,fix,pred,succ,origin=xl("O2") REG=[t for t in T if typ[t]!="Summary"] SUM=[t for t in T if typ[t]=="Summary"] ES={t:0.0 for t in T} EF={t:dur[t] for t in T} CD=dur.copy() lim=max(10,len(T)*4) for _ in range(lim): ch=False for t in REG: s=0.0 for p,r,l in pred[t]: if typ[p]=="Summary": raise ValueError( t+" cannot depend on Summary task "+p ) if r=="FS": x=EF[p]+l elif r=="SS": x=ES[p]+l elif r=="FF": x=EF[p]+l-dur[t] else: x=ES[p]+l-dur[t] s=max(s,x) if fix[t] is not None: s=fix[t] f=s+dur[t] if s!=ES[t] or f!=EF[t]: ES[t],EF[t]=s,f ch=True if not ch: break else: raise ValueError( "Forward pass did not converge; check dependency cycles" ) # Keep fixed-start overrides, but expose violated ties in worksheet output. WARN={t:[] for t in T} for t in REG: for p,r,l in pred[t]: left,right=(ES[t],EF[p]+l) if r=="FS" else (ES[t],ES[p]+l) if r=="SS" else (EF[t],EF[p]+l) if r=="FF" else (EF[t],ES[p]+l) if left+1e-9<right: WARN[t].append(t+": fixed start conflicts with "+p+" "+r+" (shortfall "+str(round(right-left,4))+" weeks)") PF=max(EF[t] for t in REG) LF={t:PF for t in T} LS={t:PF-dur[t] for t in T} for _ in range(lim): ch=False for t in reversed(REG): f=PF for s,r,l in succ[t]: if r=="FS": x=LS[s]-l elif r=="SS": x=LS[s]-l+dur[t] elif r=="FF": x=LF[s]-l else: x=LF[s]-l+dur[t] f=min(f,x) s=f-dur[t] if s!=LS[t] or f!=LF[t]: LS[t],LF[t]=s,f ch=True if not ch: break else: raise ValueError("Backward pass did not converge; check schedule inputs") for t in SUM: ss=[ ES[p]+l for p,r,l in pred[t] if r=="SS" ] ff=[ EF[p]+l for p,r,l in pred[t] if r=="FF" ] if not ss: raise ValueError( t+" Summary requires at least one SS anchor" ) if not ff: raise ValueError( t+" Summary requires at least one FF anchor" ) ES[t]=min(ss) EF[t]=max(ff) if EF[t]<ES[t]: raise ValueError( t+" Summary finish is before its start" ) CD[t]=EF[t]-ES[t] LS[t]=ES[t] LF[t]=EF[t] TFF={ t:"" if typ[t]=="Summary" else round(LF[t]-EF[t],4) for t in T } CRIT={ t:False if typ[t]=="Summary" else TFF[t]<=0.001 for t in T } START={ t:origin+pd.Timedelta(weeks=ES[t]) for t in T } FINISH={ t:origin+pd.Timedelta(weeks=EF[t]) for t in T } # Free float: move this task without moving successor early dates. # The current project finish is an implicit bound for every ordinary task. # Keep negative slack visible when fixed starts contradict relationships. FREE={} for t in T: if typ[t]=="Summary": FREE[t]="" continue slack=[PF-EF[t]] for s,r,l in succ[t]: x=(ES[s]-EF[t]-l if r=="FS" else ES[s]-ES[t]-l if r=="SS" else EF[s]-EF[t]-l if r=="FF" else EF[s]-ES[t]-l) slack.append(x) FREE[t]=round(min(slack),4) (T,typ,CD,ES,EF,START,FINISH,TFF,CRIT,WARN,LS,LF,FREE) | Cell Q2 | T,typ,CD,ES,EF,START,FINISH,TFF,CRIT,WARN,LS,LF,FREE=xl("P2") pd.DataFrame({ "CalcDuration":[round(CD[t],4) for t in T], "Start":[START[t] for t in T], "Finish":[FINISH[t] for t in T], "EarlyStart":[round(ES[t],4) for t in T], "EarlyFinish":[round(EF[t],4) for t in T], "LateStart":["" if typ[t]=="Summary" else round(LS[t],4) for t in T], "LateFinish":["" if typ[t]=="Summary" else round(LF[t],4) for t in T], "FreeFloat":[FREE[t] for t in T], "TotalFinishFloat":[TFF[t] for t in T], "IsCritical":[CRIT[t] for t in T] }) | Cell CL2 | schedule=xl("P2") pd.DataFrame({"ScheduleWarning":["; ".join(schedule[9][t]) for t in schedule[0]]})